Agent Incubation Platform

Realistic Project Plan  ·  v1.0

Ravichandran Kanakasikamani  ·  Empower  ·  April 2026

EXECUTIVE SUMMARY

This plan describes a phased build of the Agent Incubation Platform — an internal system that lets developers build governed AI agents and business users safely pilot and adopt them. The governance engine (agent-foundry) is already built and tested. What remains is the autonomy layer, real system connectors, and a two-sided portal.

| ~8 months Total timeline | Week 8 First value delivered | 3–4 people Team size | 4 Phases |
| --- | --- | --- | --- |

ASSUMPTIONS

This plan is scoped assuming the following are in place:

- Deployment access to a shared internal environment is available from day one

- Microsoft 365 / Outlook Graph API credentials are accessible for the email triage pilot

- Access to a Pega development instance and/or ServiceNow sandbox is available by Phase 1

- A dedicated team of 3–4 engineers can be allocated, with part-time EA involvement

- Business stakeholders (ops team) are available for 1–2 hours/week to review shadow logs during Phase 1

- Enterprise architecture and security review can be scheduled within the Phase 1–2 gate period

- LLM API access (Claude or equivalent) is approved for internal use

| 0 | Foundation — Lock the Architecture | Now · Weeks 1–2 |
| --- | --- | --- |

Goal: Establish the technical foundation everything else builds on. No visible output to business users yet — but if this is wrong, everything downstream is wrong.

### What gets built

- AutonomyLevel as a first-class concept in agent-foundry (Shadow / HITL / Confidence / HOTL)

- Shadow mode — all Tier 4+ effects route to a no-op audit sink. Agent runs but executes nothing.

- HarnessBuilder and RuntimeBuilder — clean one-line swap from sandbox to production wiring

- RuntimeConfig — reads all connector credentials from environment variables, validates at startup

- Confidence score wired as a policy metadata condition (enables L3 behaviour in Phase 2)

- Auto-demotion trigger interface — anomaly detector and kill switch hook points defined

### Who is needed

Lead engineer:  1 person full-time — agent-foundry Python work

Reviewer:  Enterprise architect — review the autonomy model and config approach

### Success criteria

- All 284 existing tests continue to pass

- Shadow mode demonstrable: email triage agent runs, logs decisions, executes nothing

- RuntimeConfig validates cleanly with placeholder env vars

| GATE | Phase 0 → 1: EA reviews AutonomyLevel design and RuntimeConfig approach. Sign-off before Phase 1 begins. |
| --- | --- |

| 1 | Prove the Loop — One Agent, Real Data | Weeks 3–8 |
| --- | --- | --- |

Goal: Get the email triage agent running on real Outlook emails in shadow mode. Business users review the decision log. Promote to Human-in-the-Loop for P3/P4 tickets by end of phase.

### What gets built

- Outlook / Microsoft 365 connector — MS Graph API, OAuth 2.0, env-var config for any tenant

- LangGraph integration — LLM node for email classification, priority inference, entity extraction

- Pega Case Management connector — REST API, config-driven, portable across Pega instances

- ServiceNow connector — Table API, config-driven, portable across ServiceNow instances

- Email triage agent wired end-to-end in shadow mode on a real inbox

- Decision log viewer — plain-English display of what the agent would have done on each email

- Promote to L2 (Human in the Loop) for P3/P4 routine ticket creation at end of Phase 1

### Who is needed

Engineers:  2 full-time — connector work + LangGraph integration

Business stakeholder:  Ops manager — 1 hr/week reviewing shadow decision logs

EA:  Available for questions on connector security and data flows

### Key milestones

Week 4:  Outlook connector live, reading emails from real inbox

Week 5:  LangGraph classifying emails (intent + priority)

Week 6:  Pega and ServiceNow connectors connected to sandbox instances

Week 7:  Full shadow pipeline running — decision log visible to ops team

Week 8:  Business review complete, accuracy sufficient, promote to L2 for P3/P4

### Success criteria

- Shadow pipeline running continuously on real inbox with zero execution errors

- Ops team reviews 2 weeks of decisions and confirms accuracy acceptable for L2

- P3/P4 ticket creation live in L2 (human approves each ticket before it's created)

| GATE | Phase 1 → 2: Business user reviews 2-week shadow log. Agrees classification accuracy is high enough to act on P3/P4 tickets. Security review of Outlook + Pega/ServiceNow data flows completed. |
| --- | --- |

| 2 | First Live Agent — Autonomous on Routine Work | Weeks 9–16 |
| --- | --- | --- |

Goal: Agent acts autonomously on P3/P4 tickets above confidence threshold. P1/P2 still human-approved. Business users see real value — tickets being created, not just logs.

### What gets built

- L3 confidence-based autonomy for P3/P4 ticket creation (auto-create when confidence ≥ 0.85)

- Pega Knowledge Buddy connector — RAG query as enrichment step before ticket draft

- Kill switch UI — operator can pause the agent or a specific effect type instantly

- Auto-demotion — anomaly detector triggers demotion from L3 to L2 when error rate spikes

- Simple metrics dashboard — tickets created, escalations, ASK rate, anomalies

- Promotion workflow — builder triggers promotion, quality gates validate automatically

- Email reply send (L2) — agent drafts acknowledgement, human approves before send

### Who is needed

Engineers:  2–3 full-time — autonomy layer, KB connector, dashboard

Business stakeholder:  Ops manager monitoring live dashboard, using kill switch if needed

EA:  Architecture review of the full autonomy model before L3 goes live

### Key milestones

Week 10:  L3 confidence-based autonomy wired and tested in harness

Week 12:  Knowledge Buddy enrichment live — tickets include KB article references

Week 13:  Kill switch UI operational, tested by ops team

Week 14:  Auto-demotion tested and verified

Week 15:  30-day stability period begins

Week 16:  30-day stability complete, EA architecture sign-off

### Success criteria

- L3 agent creating P3/P4 tickets autonomously, P1/P2 still routing to human approval

- Zero critical incidents (misrouted P1 emails, unintended external sends) in 30-day window

- Ops team comfortable with the kill switch and anomaly alerts

- EA signs off on the full architecture before Phase 3 begins

| GATE | Phase 2 → 3: Email triage agent stable at L3 for 30 days. Zero critical incidents. EA architecture sign-off granted. Second use case identified and owner committed. |
| --- | --- |

| 3 | The Platform — Open to Internal Teams | Weeks 17–28 |
| --- | --- | --- |

Goal: Generalise from one agent to many. Developer portal for publishing. Business portal for discovery and configuration without code. Second agent proves the pattern repeats.

### What gets built

- Developer portal — publish agents, set version, view metrics, manage promotion gates

- Business user portal — browse agents, configure via form (no YAML), start and monitor pilots

- Form-based configuration layer — inbox, thresholds, escalation contacts, all without code

- Multi-agent dashboard — portfolio view of all agents, their autonomy levels, metrics

- L4 Human-on-the-Loop — full autonomous mode with anomaly alerts and instant kill switches

- Second agent onboarded through the platform pipeline (not hard-coded like email triage)

- Agent catalog with plain-English descriptions and capability summaries

### Who is needed

Engineers:  3 full-time — portal frontend, platform infra, second agent

Business stakeholders:  2 teams — email triage ops (continue) + second use case owner

EA:  Ongoing architecture review as platform scope expands

PM:  Full-time — coordination, business user interviews, portal UX

### Success criteria

- Second team able to onboard and pilot an agent without engineering help beyond initial setup

- Developer portal used by at least one agent builder who wasn't part of Phase 0–2 team

- Business user portal used by ops manager to configure email triage without touching config files

- Kill switches and anomaly alerts functional across all agents in the portfolio

RESOURCE PLAN

| Role | Phase 0 | Phase 1 | Phase 2 | Phase 3 | Notes |
| --- | --- | --- | --- | --- | --- |
| Lead Engineer (FE/BE) | Full-time | Full-time | Full-time | Full-time | Core platform builder |
| Engineer 2 | — | Full-time | Full-time | Full-time | Connectors, LangGraph |
| Engineer 3 | — | — | Part-time | Full-time | Portal frontend (Phase 3) |
| PM / Owner | Part-time | Part-time | Part-time | Full-time | Ravi — all phases |
| Enterprise Architect | Review | Available | Sign-off | Ongoing | Gate approvals |
| Ops Business User | — | 1 hr/week | Monitor | Portal user | Shadow log review |
| Security Review | — | Gate 1→2 | — | Gate 2→3 | Data flow review |

RISK REGISTER

| Risk | Impact | Mitigation | Level |
| --- | --- | --- | --- |
| LLM classification accuracy below threshold | Phase 1 gate fails, delayed go-live | Start with shadow mode — tune prompts and confidence thresholds before any live actions | Medium |
| Pega/ServiceNow API access delayed | Phase 1 connector work blocked | Start with harness mock connectors; real connectors swapped in once access confirmed | Medium |
| Business user disengages from shadow review | No gate sign-off, Phase 1 stalls | Weekly 30-min review sessions, not ad-hoc; pre-schedule all 8 weeks upfront | Medium |
| EA review takes longer than 2 weeks | Phase gate delays cascade | Brief EA monthly from Phase 0 — no surprises at gate reviews | Low |
| P1 email misclassified as P3/P4 in live mode | High-severity incident missed | P1/P2 always ASK regardless of confidence score; this is enforced in policy, not agent code | Low |
| Kill switch not used in time on a bad agent run | Incorrect tickets created externally | Kill switch accessible in 2 clicks; ops team trained in Phase 2 before L3 goes live | Medium |
| Knowledge Buddy API not accessible | Phase 2 enrichment step missing | Enrichment is additive — agent works without it; KB step is enhancement not critical path | Low |

DECISIONS NEEDED FROM STAKEHOLDERS

The following decisions are needed before or during Phase 0 to avoid blockers later:

- Decision 1. Which Pega instance will be used for Phase 1 sandbox? Who provides API credentials?

- Decision 2. Which ServiceNow instance? Same question — credentials and sandbox access path.

- Decision 3. Which Outlook inbox / M365 tenant will the shadow agent monitor during Phase 1?

- Decision 4. Which LLM provider is approved for internal use? (Claude API, Azure OpenAI, or other?)

- Decision 5. Who is the named business stakeholder for Phase 1 shadow review? (Needs 1 hr/week commitment.)

- Decision 6. What is the EA review process — single document review or formal architecture board?

WHAT SUCCESS LOOKS LIKE

| Week 8 | Business user reviews 2 weeks of shadow decisions and says: "Yes, it got most of these right." Agent promoted to L2 for P3/P4 tickets. |
| --- | --- |
| Week 12 | Ops manager checks the dashboard and says: "It created 47 tickets today and I only had to approve 3." |
| Week 16 | EA reviews the full system and signs off. Zero critical incidents in 30 days. Agent promoted to L3. |
| Week 28 | A second team onboards their own agent through the platform without calling engineering. |

The governance engine is already built. The platform is the wrapper around it.